## 2024 Maintenance Schedule
THE WOODLANDS YEARLY MAINTENANCE SCHEDULE 2024
FM = Financial Manager , PM = Property Manager, HGD = Homeowner Google Drive |  |  |  |  | (updated on 6/27/2024) by AA Aran & AA Megan
Season | Task | Contractor | Completion Date | Completion Goal | Notes
Winter: January-March Q1 | ADMINISTRATION MAINTENANCE
| Walk through by the PM Quarterly | Jamar Property Management |  | End of the quarter / 2024 was conducted at the end of March | 1) rule violation notice & enforcement letters sent to homeowners by PM 2) If violation isn't corrected in 30 days, PM will have a contractor complete the task, send the FM invoice for the HOA to pay and homeowner will be assessed the amount.
| Website & HGD Update Quarterly | Admin Assistant Team & Board | Late March | Due March 1st | 1) Board members must review and download meeting minutes from the Board/Partner Google Drive, change document to a pdf format, then upload in an HOA Request 2) Items required for admin team to complete task: open board meeting minutes, town hall meeting minutes, annual meeting minutes, and any special meeting minutes. 3) Admin/Board meeting discuss any text changes needed to the website as well. 4) When needed, admin team can schedule with tech professional for assistance.
| Contact List Update Quarterly | Admin Assistant Team & FM | Late March | Due by March 1st | Admin Assistant team put in an HOA Request and forward to the FM & then PM. After the documents are received, the confidential list goes on the Board/Partner Google Drive and the public list goes on the HGD. Note: the financial manager is sent the update contact information when a unit is sold.
| Welcome packets sent to new homeowners Quarterly | Jamar Property Management | N/A | Quarterly when given the contact list | Admin Assistant team put in an HOA Request and forward it to the PM (with the contact lists and the most up-to-date welcome packet with shipping instructions).
| Newsletters Mailed by USPS Quarterly | Admin Assistant Team | Late March | Due March 1st | 1) Admin Assistant team use the standard 4 season quarterly newsletter format (which includes legal requirements) and take any new/updated content from announcements 2) Admin Assistant team put in an HOA Request with the pdf version of the newsletter to go out and after a board member says it is good to go, forward to the PM to mail.
| Email Announcements HOA weekly | Admin Assistant Team | weekly | weekly | 1) Admin Assistant team updates the running announcement document and board members can review and put in suggested updates and/or changes 2) Review with HOA board at weekly admin/board meeting & email on Wednesday
| Committee Reports Monthly | Admin Assistant Team |  | Due 1st of the month | Committee member to submit committee report on the first of the month through the HOA Request system & include any questions and/or feedback from the HOA in the report. The Admin Assistant team puts these reports on the HGD.
| PM / Admin Meeting Weekly | Admin Assistant Team & PM |  | weekly | Admin Assistant team meets with the PM weekly to review HOA Requests & Large Repairs
| Internal Financial Audit Quarterly | Board Member |  | Due March 1st | Audit from last quarter completed by this time, board member report out at meeting
| Homeowner Feedback Survey Report Quarterly | Board Member | June 25th | Due before the Quarterly Townhall Meeting | Board member pulls data from the google survey, removes any identifying information or personal conflicts & puts the survey on the HGD. This survey is on the website and needs no further updating. The survey data is time stamped and call be pulled from he most recent results.
| Property Manager Report Monthly | PM & Admin Assistant Team |  | Before the monthly open board meeting | PM puts a pdf monthly property manager report in an HOA Request and the Admin Assistant team uploads the document to the HGD.
| Large Repair Schedule Quarterly | Admin Assistant Team with PM & Contractor (Engineer) |  | By the end of the quarter | Admin Assistant Team / PM / Engineer meet to see where they are with large repair projects and determine what communication needs to go out to the neighborhood.
| HOA Board / Admin Meeting Weekly | Board Members & Admin Team |  | weekly meeting | Admin Assistant team and HOA Board meets weekly over zoom to review the weekly announcements, HOA Requests, Large Repairs, legal business & any other concerns.
| Meeting Agenda Monthly | Board Members & Admin Team |  | Due the 1st of the Month | Board members must put a PDF version of their meeting agenda (both the PPT & Word Doc) in an HOA Request by the 1st of the month, so the admin team can put it on the website & HGD.
| Distribute cold weather guidelines reminder | Admin Assistant Team |  | By the end of January | Admin Assistant team adds to the weekly announcements & quarterly newsletter.
| Open Board Meeting Monthly & Town Hall Meeting Quarterly | Board/ Admins / PM / FM |  | Each month/quarter | Monthly Open board meeting on the 2nd Thursday of the month from 7-8:30pm on HOA zoom (Meeting ID 9202320239) and Quarterly Town Hall on the 3rd Thursday of the month from 7-8:30pm on HOA zoom (no meetings in December for holidays)
PROPERTY MAINTENANCE
| Spigot Covers Install Yearly | PM Maintenance Team |  | By Jan 1st or cold weather | Spigot covers put on spigots by the time cold weather hits
| Clean Trash Corrals Monthly | PM Maintenance Team |  | Monthly
| Refill & Clean Dog Bag Stations Weekly | PM Maintenance Team |  | Weekly
| Spring clean up before landscaping services start ~ once spring | R&S Landscaping |  | Before landscaping work starts in March | Landscaping contract runs March-December (10 months out of the year)
| Mulch Opt Out List | Admin Assistant Team |  | Due by March 1st | 1) Opt out of mulch survey on The Woodlands website www.woodlandshoa.net 2) Homeowners have until March 1st to fill out the survey to opt out of mulch 3) Admin Assistant Team to pull the survey data March 2nd & send document in an HOA Request to the PM (PM will sent to the landscapers)
| Snow removal from parking lot as needed | R&S Landscaping |  | During Storms
| Salt parking lot as needed | R&S Landscaping |  | During Storms
| Salt and shover sidewalks as needed | PM Maintenance Team |  | During Storms
Season | Task | Contractor | Completion Date | Completion Goal | Notes
Spring: April-June Q2 | ADMINISTRATION MAINTENANCE
| Walk through by the PM Quarterly | Jamar Property Management |  | End of the quarter / 2024 was conducted at the end of March | 1) rule violation notice & enforcement letters sent to homeowners by PM 2) If violation isn't corrected in 30 days, PM will have a contractor complete the task, send the FM invoice for the HOA to pay and homeowner will be assessed the amount.
| Website & HGD Update Quarterly | Admin Assistant Team & Board |  | Due March 1st | 1) Board members must review and download meeting minutes from the Board/Partner Google Drive, change document to a pdf format, then upload in an HOA Request 2) Items required for admin team to complete task: open board meeting minutes, town hall meeting minutes, annual meeting minutes, and any special meeting minutes. 3) Admin/Board meeting discuss any text changes needed to the website as well. 4) When needed, admin team can schedule with tech professional for assistance.
| Contact List Update Quarterly | Admin Assistant Team & FM |  | Due by March 1st | Admin Assistant team put in an HOA Request and forward to the FM & then PM. After the documents are received, the confidential list goes on the Board/Partner Google Drive and the public list goes on the HGD. Note: the financial manager is sent the update contact information when a unit is sold.
| Welcome packets sent to new homeowners Quarterly | Jamar Property Management |  | Quarterly when given the contact list | Admin Assistant team put in an HOA Request and forward it to the PM (with the contact lists and the most up-to-date welcome packet with shipping instructions).
| Newsletters Mailed by USPS Quarterly | Admin Assistant Team |  | Due March 1st | 1) Admin Assistant team use the standard 4 season quarterly newsletter format (which includes legal requirements) and take any new/updated content from announcements 2) Admin Assistant team put in an HOA Request with the pdf version of the newsletter to go out and after a board member says it is good to go, forward to the PM to mail.
| Email Announcements HOA weekly | Admin Assistant Team |  | weekly | 1) Admin Assistant team updates the running announcement document and board members can review and put in suggested updates and/or changes 2) Review with HOA board at weekly admin/board meeting & email on Wednesday
| Committee Reports Monthly | Admin Assistant Team |  | Due 1st of the month | Committee member to submit committee report on the first of the month through the HOA Request system & include any questions and/or feedback from the HOA in the report. The Admin Assistant team puts these reports on the HGD.
| PM / Admin Meeting Weekly | Admin Assistant Team & PM |  | weekly | Admin Assistant team meets with the PM weekly to review HOA Requests & Large Repairs
| Internal Financial Audit Quarterly | Board Member |  | Due March 1st | Audit from last quarter completed by this time, board member report out at meeting
| Homeowner Feedback Survey Report Quarterly | Board Member | June 25th | Due before the Quarterly Townhall Meeting | Board member pulls data from the google survey, removes any identifying information or personal conflicts & puts the survey on the HGD. This survey is on the website and needs no further updating. The survey data is time stamped and call be pulled from he most recent results.
| Property Manager Report Monthly | PM & Admin Assistant Team |  | Before the monthly open board meeting | PM puts a pdf monthly property manager report in an HOA Request and the Admin Assistant team uploads the document to the HGD.
| Large Repair Schedule Quarterly | Admin Assistant Team with PM & Contractor (Engineer) |  | By the end of the quarter | Admin Assistant Team / PM / Engineer meet to see where they are with large repair projects and determine what communication needs to go out to the neighborhood.
| HOA Board / Admin Meeting Weekly | Board Members & Admin Team |  | weekly meeting | Admin Assistant team and HOA Board meets weekly over zoom to review the weekly announcements, HOA Requests, Large Repairs, legal business & any other concerns.
| Meeting Agenda Monthly | Board Members & Admin Team |  | Due the 1st of the Month | Board members must put a PDF version of their meeting agenda (both the PPT & Word Doc) in an HOA Request by the 1st of the month, so the admin team can put it on the website & HGD.
| Open Board Meeting Monthly & Town Hall Meeting Quarterly | Board/ Admins / PM / FM |  | Each month/quarter | Monthly Open board meeting on the 2nd Thursday of the month from 7-8:30pm on HOA zoom (Meeting ID 9202320239) and Quarterly Town Hall on the 3rd Thursday of the month from 7-8:30pm on HOA zoom (no meetings in December for holidays)
| Spigot Covers Removal Yearly | PM Maintenance Team |  | By April 1 or warm weather | Spigot covers removed from spigots by the time cold weather hits
| HOA Garage clean/organize & Inventory List Yearly | Board |  | By the end of the quarter | Board members must clean/organize and make an inventory list of the HOA Garage items. Label all HOA items in the garage. Ask for replacement items in an HOA Request and reach out the FM to get the last year's financial documents to be kept in the locked filing cabinet int the garage. Then give the old documents (7 years plus that aren't being kept for historical perspective) to the volunteer homeowner to shred.
| Spring Community Garage Sale | Board/Committee |  | June | Volunteer garage sale event organized by homeowner volunteers
PROPERTY MAINTENANCE
| Bush trim spring & fall | R&S Landscaping |  | Early spring
| Clear fallen branches from property monthly | R&S Landscaping |  | Monthly | If needed more than once per month or after a large storm, can add in for an hourly rate
| Cut/mow grass and edge common areas and sidewalks on growing season weekly | R&S Landscaping |  | Weekly
| Cedar mulch spread in common area beds and the fronts of units ~ once spring | R&S Landscaping |  | Mid Spring | Cedar mulch = natural insect repellent
| Clean and patch potholes in parking lot | PM Maintenance Team |  | By end of quarter
| Weeding beds and areas to parking lot | Volunteers currently |  |  | Hopefully herbaceous invasive management moves to contractor Deep Roots with native plantings once the pond area repair is complete
| Gutter/downspout inspection and cleaning | PM Maintenance Team |  | By end of quarter
| Refresh paint on parking spaces and unit numbers | PM Maintenance Team |  | By end of quarter
| Neighborhood-wide check for woodpecker holes (fill/patch as needed) | PM Maintenance Team |  | By end of quarter
| Clean Storm Drains Monthly | PM Maintenance Team |  | Monthly | Monthly in the Spring / Summer / Fall
| Refill & Clean Dog Bag Stations Weekly | PM Maintenance Team |  | Weekly
| Clean Trash Corrals Monthly | PM Maintenance Team |  | Monthly
| Tree Report Annual | Bluestone Tree |  | May | Yearly assessment & tree report conducted in May. Any recommendations for injections conducted in June, tree removals asap & tree trimming in the fall.
Season | Task | Contractor | Completion Date | Completion Goal | Notes
Summer: July-September Q3 | ADMINISTRATION MAINTENANCE
| Walk through by the PM Quarterly | Jamar Property Management |  | End of the quarter / 2024 was conducted at the end of March | 1) rule violation notice & enforcement letters sent to homeowners by PM 2) If violation isn't corrected in 30 days, PM will have a contractor complete the task, send the FM invoice for the HOA to pay and homeowner will be assessed the amount.
| Website & HGD Update Quarterly | Admin Assistant Team & Board |  | Due March 1st | 1) Board members must review and download meeting minutes from the Board/Partner Google Drive, change document to a pdf format, then upload in an HOA Request 2) Items required for admin team to complete task: open board meeting minutes, town hall meeting minutes, annual meeting minutes, and any special meeting minutes. 3) Admin/Board meeting discuss any text changes needed to the website as well. 4) When needed, admin team can schedule with tech professional for assistance.
| Contact List Update Quarterly | Admin Assistant Team & FM |  | Due by March 1st | Admin Assistant team put in an HOA Request and forward to the FM & then PM. After the documents are received, the confidential list goes on the Board/Partner Google Drive and the public list goes on the HGD. Note: the financial manager is sent the update contact information when a unit is sold.
| Welcome packets sent to new homeowners Quarterly | Jamar Property Management |  | Quarterly when given the contact list | Admin Assistant team put in an HOA Request and forward it to the PM (with the contact lists and the most up-to-date welcome packet with shipping instructions).
| Newsletters Mailed by USPS Quarterly | Admin Assistant Team |  | Due March 1st | 1) Admin Assistant team use the standard 4 season quarterly newsletter format (which includes legal requirements) and take any new/updated content from announcements 2) Admin Assistant team put in an HOA Request with the pdf version of the newsletter to go out and after a board member says it is good to go, forward to the PM to mail.
| Email Announcements HOA weekly | Admin Assistant Team |  | weekly | 1) Admin Assistant team updates the running announcement document and board members can review and put in suggested updates and/or changes 2) Review with HOA board at weekly admin/board meeting & email on Wednesday
| Committee Reports Monthly | Admin Assistant Team |  | Due 1st of the month | Committee member to submit committee report on the first of the month through the HOA Request system & include any questions and/or feedback from the HOA in the report. The Admin Assistant team puts these reports on the HGD.
| PM / Admin Meeting Weekly | Admin Assistant Team & PM |  | weekly | Admin Assistant team meets with the PM weekly to review HOA Requests & Large Repairs
| Internal Financial Audit Quarterly | Board Member |  | Due March 1st | Audit from last quarter completed by this time, board member report out at meeting
| Homeowner Feedback Survey Report Quarterly | Board Member |  | Due before the Quarterly Townhall Meeting | Board member pulls data from the google survey, removes any identifying information or personal conflicts & puts the survey on the HGD. This survey is on the website and needs no further updating. The survey data is time stamped and call be pulled from he most recent results.
| Property Manager Report Monthly | PM & Admin Assistant Team |  | Before the monthly open board meeting | PM puts a pdf monthly property manager report in an HOA Request and the Admin Assistant team uploads the document to the HGD.
| Large Repair Schedule Quarterly | Admin Assistant Team with PM & Contractor (Engineer) |  | By the end of the quarter | Admin Assistant Team / PM / Engineer meet to see where they are with large repair projects and determine what communication needs to go out to the neighborhood.
| HOA Board / Admin Meeting Weekly | Board Members & Admin Team |  | weekly meeting | Admin Assistant team and HOA Board meets weekly over zoom to review the weekly announcements, HOA Requests, Large Repairs, legal business & any other concerns.
| Meeting Agenda Monthly | Board Members & Admin Team |  | Due the 1st of the Month | Board members must put a PDF version of their meeting agenda (both the PPT & Word Doc) in an HOA Request by the 1st of the month, so the admin team can put it on the website & HGD.
| Finance Committee Submit Proposed Budgets to the HOA | Volunteer Committee Members |  | By July 1st | Operations budget & Reserve Budget submitted by committee for board to review and update before the annual meeting
| Prepare for annual meetings (reports) | Board |  | Oct 1st | Board members to put their reports in the meeting agenda by the 1st of the month
| Distribute notice for annual meeting in October with proposed budgets & Elections documents (if election year) | Admin Assistant Team & board |  | Must be mailed between September 11th-30th | 1) Governing documents require this mailed USPS notice to be sent to all homeowners between 10 & 30 days prior to the annual meeting. 2) Board members must put in an HOA Request by August 15th with meeting notice, proposed operational & reserve budget, include ballot/candidate statements on election year & proposed operational & reserve budgets 3) Board & Admin team must review all these legal documents with the legal team prior 4) Board members must pull candidate statements from the website
| Open Board Meeting Monthly & Town Hall Meeting Quarterly | Board/ Admins / PM / FM |  | Each month/quarter | Monthly Open board meeting on the 2nd Thursday of the month from 7-8:30pm on HOA zoom (Meeting ID 9202320239) and Quarterly Town Hall on the 3rd Thursday of the month from 7-8:30pm on HOA zoom (no meetings in December for holidays)
| Fall Community Volunteer Day | Board/Committee |  | September | Fall Community Volunteer Day organized by volunteer Homeowners
PROPERTY MAINTENANCE
| Clean Trash Corrals Monthly | PM Maintenance Team |  | Monthly
| Refill & Clean Dog Bag Stations Weekly | PM Maintenance Team |  | Weekly
| Clean Storm Drains Monthly | PM Maintenance Team |  | Monthly | Monthly in the Spring / Summer / Fall
| Cut/mow grass and edge common areas and sidewalks on growing season weekly | R&S Landscaping |  | Weekly
| Clear fallen branches from property monthly | R&S Landscaping |  | Monthly | If needed more than once per month or after a large storm, can add in for an hourly rate
| Clean and patch potholes in parking lot | PM Maintenance Team |  | By end of quarter
| Weeding beds and areas to parking lot | Volunteers currently |  |  | Hopefully herbaceous invasive management moves to contractor Deep Roots with native plantings once the pond area repair is complete
| Schedule chimney inspection for October | Admin Assistant Team & PM |  | By end of quarter | Get specific dates for inspection (PM to talk to the contractor) and update those dates on the chimney inspection survey and any communication (email/newsletter)
| Tree Trimming & Removals | Bluestone Tree |  | By end of fall | Recommended tree removals asap & tree trimming in the fall (around September usually)
| Chimney Inspection Homeowner List | Admin Assistant Team |  | Due by Sept 1 | 1) Chimney Inspection survey on The Woodlands website www.woodlandshoa.net 2) Homeowners have until Sept 1st to fill out the survey if they want to be home during the inspection 3) Admin Assistant Team to pull the survey data Sept 2nd & send document in an HOA Request to the PM (PM will sent to the landscapers) 4) HOA will pay the cost of inspection & Homeowners chimney will be cleaned if needed and then their account will be assessed the cost of the cleaning. Internal chimney repairs are the homeowner's responsibility. 5) Contractor will submit a report. If the homeowner puts in an HOA Request, they can be given their portion of the chimney inspection report, as the rest is confidential.
Season | Task | Contractor | Completion Date | Completion Goal | Notes
Fall: October-December Q4 | ADMINISTRATION MAINTENANCE
| Walk through by the PM Quarterly | Jamar Property Management |  | End of the quarter / 2024 was conducted at the end of March | 1) rule violation notice & enforcement letters sent to homeowners by PM 2) If violation isn't corrected in 30 days, PM will have a contractor complete the task, send the FM invoice for the HOA to pay and homeowner will be assessed the amount.
| Website & HGD Update Quarterly | Admin Assistant Team & Board |  | Due March 1st | 1) Board members must review and download meeting minutes from the Board/Partner Google Drive, change document to a pdf format, then upload in an HOA Request 2) Items required for admin team to complete task: open board meeting minutes, town hall meeting minutes, annual meeting minutes, and any special meeting minutes. 3) Admin/Board meeting discuss any text changes needed to the website as well. 4) When needed, admin team can schedule with tech professional for assistance.
| Contact List Update Quarterly | Admin Assistant Team & FM |  | Due by March 1st | Admin Assistant team put in an HOA Request and forward to the FM & then PM. After the documents are received, the confidential list goes on the Board/Partner Google Drive and the public list goes on the HGD. Note: the financial manager is sent the update contact information when a unit is sold.
| Welcome packets sent to new homeowners Quarterly | Jamar Property Management |  | Quarterly when given the contact list | Admin Assistant team put in an HOA Request and forward it to the PM (with the contact lists and the most up-to-date welcome packet with shipping instructions).
| Newsletters Mailed by USPS Quarterly | Admin Assistant Team |  | Due March 1st | 1) Admin Assistant team use the standard 4 season quarterly newsletter format (which includes legal requirements) and take any new/updated content from announcements 2) Admin Assistant team put in an HOA Request with the pdf version of the newsletter to go out and after a board member says it is good to go, forward to the PM to mail.
| Email Announcements HOA weekly | Admin Assistant Team |  | weekly | 1) Admin Assistant team updates the running announcement document and board members can review and put in suggested updates and/or changes 2) Review with HOA board at weekly admin/board meeting & email on Wednesday
| Committee Reports Monthly | Admin Assistant Team |  | Due 1st of the month | Committee member to submit committee report on the first of the month through the HOA Request system & include any questions and/or feedback from the HOA in the report. The Admin Assistant team puts these reports on the HGD.
| PM / Admin Meeting Weekly | Admin Assistant Team & PM |  | weekly | Admin Assistant team meets with the PM weekly to review HOA Requests & Large Repairs
| Internal Financial Audit Quarterly | Board Member |  | Due March 1st | Audit from last quarter completed by this time, board member report out at meeting
| Homeowner Feedback Survey Report Quarterly | Board Member |  | Due before the Quarterly Townhall Meeting | Board member pulls data from the google survey, removes any identifying information or personal conflicts & puts the survey on the HGD. This survey is on the website and needs no further updating. The survey data is time stamped and call be pulled from he most recent results.
| Property Manager Report Monthly | PM & Admin Assistant Team |  | Before the monthly open board meeting | PM puts a pdf monthly property manager report in an HOA Request and the Admin Assistant team uploads the document to the HGD.
| Large Repair Schedule Quarterly | Admin Assistant Team with PM & Contractor (Engineer) |  | By the end of the quarter | Admin Assistant Team / PM / Engineer meet to see where they are with large repair projects and determine what communication needs to go out to the neighborhood.
| HOA Board / Admin Meeting Weekly | Board Members & Admin Team |  | weekly meeting | Admin Assistant team and HOA Board meets weekly over zoom to review the weekly announcements, HOA Requests, Large Repairs, legal business & any other concerns.
| Meeting Agenda Monthly | Board Members & Admin Team |  | Due the 1st of the Month | Board members must put a PDF version of their meeting agenda (both the PPT & Word Doc) in an HOA Request by the 1st of the month, so the admin team can put it on the website & HGD.
| Attend annual meeting and vote on budgets | Board/ Admins / PM / FM |  | 2nd Thurs in October
| Open Board Meeting Monthly & Town Hall Meeting Quarterly | Board/ Admins / PM / FM |  | Each month/quarter | Monthly Open board meeting on the 2nd Thursday of the month from 7-8:30pm on HOA zoom (Meeting ID 9202320239) and Quarterly Town Hall on the 3rd Thursday of the month from 7-8:30pm on HOA zoom (no meetings in December for holidays)
| HOA Request Form Yearly Update | Admin Assistants, technology specialist |  | By the end of the quarter | Work with the tech specialist to update and put up the new HOA Request form Jan 1 of the next year. Board members can give feedback at the admin meeting, but this is not a board task and the sole functionality and responsibility falls on the admins.
| Review contracts and sign new contracts yearly | Board/ Admins / PM / FM |  | By the end of the quarter | Review & prioritize 3 year contracts to give all professionals and volunteer board members time to adequately negotiate them. Major partners: Bluestone, Jamar, Legal, FM, R&S Lawncare
| Letter from FM for HOA Fees Yearly | FM/Admins/Board |  | By the end of the quarter | FM to mail all Homeowners a schedule of HOA fees for the next year to include: 1) Monthly HOA fees and how to see/pay them on the website 2) Yearly Insurance due date 3) Any special assessment amounts & due dates (if applicable) 4) A reminder of the Delinquency Policy Resolution (DPR) on the website
PROPERTY MAINTENANCE
| Chimney Inspections (October) | Julie Todd LLC |  | By the end of October | Chimney inspections
| Clean Storm Drains Monthly | PM Maintenance Team |  | Monthly | Monthly in the Spring / Summer / Fall
| Bush trim spring & fall | R&S Landscaping |  | Early spring
| Clean Trash Corrals Monthly | PM Maintenance Team |  | Monthly
| Refill & Clean Dog Bag Stations Weekly | PM Maintenance Team |  | Weekly
| Weeding beds and areas to parking lot | Volunteers currently |  |  | Hopefully herbaceous invasive management moves to contractor Deep Roots with native plantings once the pond area repair is complete
| Cut/mow grass and edge common areas and sidewalks on growing season weekly | R&S Landscaping |  | Weekly
Leaf removal twice as leaves fall & Mulch leaves in grassy areas (with lawn mower)
Clean gutters and storm drains of leaves and debris
Snow removal from parking lot as needed
Salt entrances and parking lot as needed
| Clear fallen branches from property monthly | R&S Landscaping |  | Monthly | If needed more than once per month or after a large storm, can add in for an hourly rate
| Snow removal from parking lot as needed | R&S Landscaping |  | During Storms
| Salt parking lot as needed | R&S Landscaping |  | During Storms
| Salt and shover sidewalks as needed | PM Maintenance Team |  | During Storms

## Current Contracts
THE WOODLANDS VENDORS / CONTRACTS
Vendor | Services | Notes
CONTRACTED CONTRACTORS
Abrams & Moss | Chelsea Abrams | Civil engineering, grading, drainage, representative to the City, helpful for obsolete pond issues/ central stormwater drainage area, project management for drainage (both central and units)
Bluestone Tree (Certified Arborists) |  | Yearly tree report, tree injections, tree trimming, tree removals & woody invasive management.
Comer Nowling | Taxes
David Martin |  | Website hosting & Technology Support
Jamar Property Management | Property Manager | 3 year contract. 2024/2025/2026. Monthly base pay of $2,000. Special projects at additional hourly cost. $1,500 discretionary approval for neighborhood needs. Ashley as the primary contact.
Julie Todd LLC | Cleaning/Inspections/Pest Control | Fall chimney inspections required for all units 3 year contract 2024/2025/2025. $50 per unit: $3,300 per year paid by HOA. Cleaning unit chimney for $115, billed to HOA and assesed to homeowners. Any chimney repairs a matter for homeowners to schedule themselves. Pest prevention/control fall and spring (spiderweb removal and spraying).
Megan Payton | Admin Assistant | up to 20 hours a week at $18 per hour
Maintenance needs: In-house with Jamar Property Management | General Property needs and external/common area repairs: Includes filling in woodpecker holes, cleaning gutters and other | $55 per hour
kristie Weddle | Admin Assistant | up to 25 hours a week at $18 per hour
R&S Landscaping |  | Landscaping contract and snow removal contract. 3 year contract for both items 2024/2025/2026. Grass cutting, cedar mulch in spring for common area beds and fronts of units, wood chip trail spray and add chips spring and fall, bush trimming spring and fall, trash/debris clean up day spring, monthly branches pickup (and after a big storm as needed for an extra fee), leaf removal on strees, sidewalks, fronts of units, wood chip path area, leave shred on back of property.
Stephen & Laurie Miller CPA | Financial Manager
RSI | Reserve Study | 2024 (needs to be conducted every 3 years). Updated long term repair and cost projections for The Woodlands.
Taycon | Obsolete Pond Area Repair | Construction items
Deep Roots | Stormwater Drainage Area landscaping & maintenance, planting naitives in the common areas & external areas, herbaceous invasive management in the common areas & external areas.
AS NEEDED CONTRACTORS
Bruce Garage Door Inc |  | Garage door repair: as needed
EcoLogic |  | Naitive plantings & herbaceous invasive plant removal, helped with the modified biorention area design
J&S Locksmith |  | Locksmith: As needed
McCoin Roofing |  | Roofing, chimney flashing, repair, roof leaks: as needed
Roto Rooter |  | Plumbing and common area private drain clearing: as needed
Sherlock Homes Inspections |  | Used in 2015 for subwide inspection: as needed
Terminix |  | Pest control, termite inspections and treatments: as needed

## 2023 Large Projects
THE WOODLANDS LARGE PROJECTS Tracking
Large Projects | Building/Unit Number | Contractor | Estimated Cost | Completion Status | Notes
Roof |  |  |  |  | New roofs were put on in 2020/2021/2022, shouldn't need for another 20 years or so
Grading
Sidewalk
Drainage |  |  |  |  | 2024/2025/2026 Community Wide Drainage Project to happen after obsolete pond area repaired (this includes grading, new sidewalks foundation drains and some waterproofing of buildings)
Obsolete Pond area |  | Taycon & Deep Roots |  |  | 2024 working on this project
Woodchip trail restoration |  |  |  |  | Completed in 2023, spring and fall maintenance in contract with R& S Landscaping
Hammock area
Foundation drains |  |  |  |  | 2024/2025/2026 Foundation drains need to be replaced for all the buildings asap
Green space common area
Pavement common area by HOA garage
Siding |  |  |  |  | Deteriorating rapidly ~ needs a complete replacement by 2029 at the latest, estimated cost is $100,000 per building for wood colored cement siding (Longest lasting and cost efficient option)
Benches restoration
Picnic table restoration
Decks: Buildings |  |  |  |  | 3 buildings worth of decks repaired/power washed/stained every year. Start at building 1 and move up through building 14. This year the required power wash / stain every 5 years is continually met. 2024: Buildings 1-3, 2025: Buildings 4-6, 2026: Buildings 7-9, 2027: Buildings 10-12 2028: Buidings 12-14 ~ start over again: 2029: Buildings 1-3, 2030: Buildings 4-6
Dog bag stations restorations |  |  |  |  | Complete in 2023, keep up maintenance
Repair common decks and fences, powerwash and stain original decks and fences (common area and individual) |  |  |  |  | Complete in 2023, keep up maintenance
Roger's Road - signage |  |  |  |  | Complete in 2022, keep up maintenance
Gutter repairs |  |  |  |  | 2024: Move high gutters closer to the roofs (contractor Steve's Roofing error fix)

## 2024 Summary RSI
OLD DATA ~ AA1 TO ADD NEW DATA STILL
Reserve Item | Date | Basis Cost | Quantity | Current Cost | Est. Life | Adj. Life | Rem. Life | Future Cost
Bulidling Staining- Residence Units | 1/22-1/27 | 2500 | 66 Units | 165000 | 10:00 | 10:00 | 6:06 | 200206
Building Staining- Garages | 1/26-1/27 | 1800 | 8 Allowance | 14400 | 10:00 | 10:00 | 8:06 | 18515
Common Sidewalks- Sectional Replacement | 1/2018 | 10 | 615 Square Feet | 6150 | 5:00 | 7:00 | 0:00 | 6150
Fence Repair- Contingency | 1/2022 | 1000 | 1 Allowance | 1000 | 5:00 | 5:00 | 4:00 | 1125
Foundation Repair- Contingency | 1/2019 | 15000 | 1 Allowance | 15000 | 4:00 | 4:00 | 1:00 | 15450
Garage- Roof Replacement | 1/21-1/24 | 300 | 234 Squares | 70200 | 25:00 | 25:00 | 4:05 | 80015
Garages- Maintenance/Repair Contin | 1/2021 | 3,00 | 1 Allowance | 3000 | 5:00 | 5:00 | 3:00 | 3278
Landscape- Capital Mainenance & Upgrades | 1/2020 | 10000 | 1 Allowance | 10000 | 2:00 | 5:00 | 2:00 | 10609
Mailbox Stations | 1/2028 | 600 | 4 Each | 2400 | 20:00 | 20:00 | 10:00 | 3225
Observation Deck | 1/2026 | 24000 | 1 Allowance | 24000 | 20:00 | 20:00 | 8:00 | 30402
Reserve Study Updates | 1/2022 | 3000 | 1 Allowance | 3000 | 4:00 | 4:00 | 4:00 | 3376
Retaining Walls Repaid and Replacement | 1/2020 | 5000 | 1 Partial | 5000 | 10:00 | 10:00 | 2:00 | 5304
Roof/Gutter Replacement | 1/18-1/26 | 300 | 744 Squares | 223200 | 25:00 | 25:00 | 3:09 | 250463
Sectional Siding/Trim Repair/Replacement | 1/19-1/24 | 5000 | 6 Allowance | 30000 | 7:00 | 7:00 | 3:06 | 33312
Signage- Street and Address Replacement | 1/2025 | 3000 | 1 Total Re | 3000 | 15:00 | 15:00 | 7:00 | 3689
Streets- Asphalt Repair- Patching and Crack Seal | 1/2020 | 5000 | 1 Allowance | 5000 | 5:00 | 5:00 | 2:00 | 5304
Streets- Asphalt Resurfacing | 1/2023 | 1 | 73,500 Sq Ft | 128625 | 20:00 | 20:00 | 5:00 | 149111
Streets- Asphalt Seal Coating | 1/2024 | 0 | 73,500 Sq Ft | 11025 | 5:00 | 9:00 | 6:00 | 13164
Unit Deck Repair & Replacement | 1/2019 | 15000 | 1 Allowance | 15000 | 5:00 | 5:00 | 1:00 | 15450
Utility Main Contingency | 1/2020 | 3<000 | 1 Allowance | 3000 | 3:00 | 3:00 | 2:00 | 3182

## 2024 Data RSI
Expidenture |  |  |  | OLD DATA ~ AA1 TO ADD NEW DATA STILL | Projects that have not been completed highlighted in yellow.
Date | Reserve Item | Service Date | Estimated Life | Expidenture | Notes
Year: 2018
01/01/2018 | Common Sidewalks- Sectional Replacement | 01/01/2011 | 7:00 | 6150
01/01/2018 | Roof/Gutter Replacements | 01/01/1993 | 25:00 | 19800 | gutter replacements didn't happen
25950
Year: 2019
01/01/2019 | Foudation Repair Contingency | 01/01/2015 | 4:00 | 15450
01/01/2019 | Roof/Gutter Replacements | 01/01/1994 | 25:00 | 55002 | gutter replacements didn't happen
01/01/2019 | Sectional Siding/Trim Repair/Replacement | 01/01/2012 | 7:00 | 5150
01/01/2019 | Unit Deck Repair & Replacement | 01/01/2014 | 5:00 | 15450
91052
Year: 2020
01/01/2020 | Landscape- Capital Maintenance & Upgrades | 01/01/2015 | 5:00 | 10609
01/01/2020 | Retaining Walls Repair and Replacement | 01/01/2010 | 10:00 | 5304.5
01/01/2020 | Sectional Siding/Trim Repair/Replacement | 01/01/2013 | 7:00 | 5304.5
01/01/2020 | Streets-Asphalt Repair-Patching and Cracks | 01/01/2015 | 5:00 | 5304.5
01/01/2020 | Utility Main Contingency | 01/01/2017 | 3:00 | 3182.7
29705.2
Year: 2021
01/01/2021 | Garage- Roof Replacement | 01/01/1996 | 25:00 | 19669.09
01/01/2021 | Garages-Maintenance/Repair Contingency | 01/01/2016 | 5:00 | 3278.18
01/01/2021 | Roof/Gutter Replacements | 01/01/1996 | 25:00 | 60318.53 | gutter replacements didn't happen
01/01/2021 | Sectional Siding/Trim Repair/Replacement | 01/01/2014 | 7:00 | 5463.64
88729.44
Year: 2022
01/01/2022 | Building Staining- Residence Units | 01/01/2012 | 10:00 | 30951.49
01/01/2022 | Fence Repair Contingency | 01/01/2017 | 5:00 | 1125.51
01/01/2022 | Garage- Roof Replacement | 01/01/1997 | 25:00 | 22285.07
01/01/2022 | Lanscape- Capital Maintenance & Upgrades | 01/01/2020 | 2:00 | 11255.09
01/01/2022 | Reserve Study Updates | 01/01/2018 | 4:00 | 3376.53
01/01/2022 | Roof/Gutter Replacements | 01/01/1997 | 25:00 | 37817.1 | gutter replacements didn't happen
01/01/2022 | Sectional Siding/Trim Repair/Replacement | 01/01/2015 | 7:00 | 5627.54
112438.33
Year: 2023
01/01/2023 | Building Staining- Residence Units | 01/01/2013 | 10:00 | 31880.04
01/01/2023 | Common Sidewalks- Sectional Replacement | 01/01/2018 | 5:00 | 7129.54
01/01/2023 | Foundation Repair Contingency | 01/01/2019 | 4:00 | 17389.11
01/01/2023 | Garage- Roof Replacement | 01/01/1998 | 25:00 | 20866.93
01/01/2023 | Sectional Siding/Trim Repair/Replacement | 01/01/2016 | 7:00 | 5796.37
01/01/2023 | Streets- Asphalt Resurfacing | 01/01/2003 | 20:00 | 149111.63
01/01/2023 | Utility Main Contingency | 01/01/2020 | 3:00 | 3477.82
235651.44
Year: 2024
01/01/2024 | Building Staining- Residence Units | 01/01/2014 | 10:00 | 32836.44
01/01/2024 | Garage- Roof Replacement | 01/01/1999 | 25:00 | 17194.35
01/01/2024 | Lanscape- Capital Maintenance & Upgrades | 01/01/2022 | 2:00 | 11940.52
01/01/2024 | Sectional Siding/Trim Repair/Replacement | 01/01/2017 | 7:00 | 5970.26
01/01/2024 | Streets-Asphalt Seal Coating | 01/01/2015 | 9:00 | 13164.43
01/01/2024 | Unit Deck Repair & Replacement | 01/01/2019 | 5:00 | 17910.78
99016.78
Year:2025
01/01/2025 | Buildling Staining- Residence Units | 01/01/2015 | 10:00 | 33821.53
01/01/2025 | Signage- Street & Address Replacement | 01/01/2010 | 15:00 | 3689.62
01/01/2025 | Streets- Asphalt Repair- Patching and Cracks | 01/01/2020 | 5:00 | 6149.37
43660.52
Year: 2026
01/01/2026 | Building Staining- Residence Units | 01/01/2016 | 10:00 | 34836.18
01/01/2026 | Building Staining- Garages | 01/01/2016 | 10:00 | 9120.74
01/01/2026 | Garages- Maintenance/Repair Contingency | 01/01/2021 | 5:00 | 3800.31
01/01/2026 | Landscape- Capital Maintenance & Upgrades | 01/01/2024 | 2:00 | 12667.7
01/01/2026 | Observation Deck | 01/01/2006 | 20:00 | 30402.48
01/01/2026 | Reserve Study Updates | 01/01/2022 | 4:00 | 3800.31
01/01/2026 | Roof/Gutter Replacements | 01/01/2001 | 25:00 | 77526.33
01/01/2026 | Sectional Siding/Trim Repair/Replacement | 01/01/2019 | 7:00 | 6333.85
01/01/2026 | Utility Main Contingency | 01/01/2023 | 3:00 | 3800.31
182288.21
Year: 2027
01/01/2027 | Building Staining- Residence Units | 01/01/2017 | 10:00 | 35881.26
01/01/2027 | Building Staining- Garages | 01/01/2017 | 10:00 | 9394.37
01/01/2027 | Fence Repair Contingency | 01/01/2022 | 5:00 | 1304.77
01/01/2027 | Foundation Repair Contingency | 01/01/2023 | 4:00 | 19571.6
01/01/2027 | Sectional Siding/Trim Repair/Replacement | 01/01/2020 | 7:00 | 6523.87
72649.23
Year: 2028
01/01/2028 | Common Sidewalks- Sectional Replacement | 01/01/2023 | 5:00 | 8265.09
01/01/2028 | Lanscape- Capital Maintenance & Upgrades | 01/01/2026 | 2:00 | 13439.16
01/01/2028 | Mailbox Stations | 01/01/2008 | 20:00 | 3225.4
01/01/2028 | Sectional Siding/Trim Repair/Replacement | 01/01/2021 | 7:00 | 6719.58
31649.23
YearL 2029
01/01/2029 | Sectional Siding/Trim Repair/Replacement | 01/01/2022 | 7:00 | 6921.17
01/01/2029 | Streets-Asphalt Seal Coating | 01/01/2024 | 5:00 | 15261.18
01/01/2029 | Unit Deck Repair & Replacement | 01/01/2024 | 5:00 | 20763.51
01/01/2029 | Utility Main Contingency | 01/01/2026 | 3:00 | 4152.7
47098.56
Year: 2030
01/01/2030 | Landscape- Capital Maintenance & Upgrades | 01/01/2028 | 2:00 | 14257.61
01/01/2030 | Reserve Study Updates | 01/01/2026 | 4:00 | 4277.28
01/01/2030 | Retaining Walls Repair and Replacement | 01/01/2020 | 10:00 | 7128.8
01/01/2030 | Sectional Siding/Trim Repair/Replacement | 01/01/2023 | 7:00 | 7128.8
01/01/2030 | Streets- Asphalt Repair- Patching and Cracks | 01/01/2025 | 5:00 | 7128.8
39921.29
Year: 2031
01/01/2031 | Foundation Repair Contingency | 01/01/2027 | 4:00 | 22028.01
01/01/2031 | Garages- Maintenance/Repair Contingency | 01/01/2026 | 5:00 | 4405.6
01/01/2031 | Sectional Siding/Trim Repair/Replacement | 01/01/2024 | 7:00 | 7342.67
33776.28
Year: 2032
01/01/2032 | Building Staining- Residence Units | 01/01/2022 | 10:00 | 41596.22
01/01/2032 | Fence Repair Contingency | 01/01/2027 | 5:00 | 1512.59
01/01/2032 | Landscape- Capital Mainenance & Upgrades | 01/01/2030 | 2:00 | 15125.9
01/01/2032 | Utility Main Contingency | 01/01/2029 | 3:00 | 4537.77
62772.48
Year: 2033
01/01/2033 | Building Staining- Residence Units | 01/01/2023 | 10:00 | 42844.1
01/01/2033 | Common Sidewalks- Sectional Replacement | 01/01/2028 | 5:00 | 9581.5
01/01/2033 | Sectional Siding/Trim Repair/Replacement | 01/01/2026 | 7:00 | 7789.84
60215.44
Year: 2034
01/01/2034 | Buildling Staining- Residence Units | 01/01/2024 | 10:00 | 44129.43
01/01/2034 | Landscape- Capital Maintenance & Upgrades | 01/01/2032 | 2:00 | 16047.06
01/01/2034 | Reserve Study Updates | 01/01/2030 | 4:00 | 4814.12
01/01/2034 | Sectional Siding/Trim Repair/Replacement | 01/01/2027 | 7:00 | 8023.53
01/01/2034 | Streets- Asphalt Seal Coating | 01/01/2029 | 5:00 | 17961.89
01/01/2034 | Unit Deck Repair & Replacement | 01/01/2029 | 5:00 | 24070.6
114776.63
Year: 2035
01/01/2035 | Buildling Staining- Residence Units | 01/01/2025 | 10:00 | 45453.31
01/01/2035 | Building Staining- Garages | 01/01/2031 | 4:00 | 24792.71
01/01/2035 | Garages- Maintenance/Repair Contingency | 01/01/2028 | 7:00 | 8264.24
01/01/2035 | Lanscape- Capital Maintenance & Upgrades | 01/01/2030 | 5:00 | 8264.24
01/01/2035 | Sectional Siding/Trim Repair/Replacement | 01/01/2032 | 3:00 | 4958.54
91733.04
Year: 2036
01/01/2036 | Building Staining- Residence Units | 01/01/2026 | 10:00 | 46816.91
01/01/2036 | Building Staining- Garages | 01/01/2026 | 10:00 | 12257.52
01/01/2036 | Garages- Maintenance/Repair Contingency | 01/01/2031 | 5:00 | 5107.3
01/01/2036 | Lanscape- Capital Maintenance & Upgrades | 01/01/2034 | 2:00 | 17024.33
01/01/2036 | Sectional Siding/Trim Repair/Replacement | 01/0/2029 | 7:00 | 8512.17
89718.23
Year: 2037
01/01/2037 | Building Staining- Residence Units | 01/01/2027 | 10:00 | 48221.42
01/01/2037 | Building Staining- Garages | 01/01/2027 | 10:00 | 12625.24
01/01/2037 | Fence Repair- Contingency | 01/01/2032 | 5:00 | 1753.51
01/01/2037 | Sectional Siding/Trim Repair/Replacement | 01/01/2030 | 7:00 | 8767.53
71367.7
Year: 2038
01/01/2038 | Common Sidewalks- Sectional Replacement | 01/01/2033 | 5:00 | 11107.58
01/01/2038 | Lanscape- Capital Maintenance & Upgrades | 01/01/2036 | 2:00 | 18061.11
01/01/2038 | Reserve Study Updates | 01/01/2034 | 4:00 | 5418.33
01/01/2038 | Sectional Siding/Trim Repair/Replacement | 01/01/2031 | 7:00 | 9030.56
01/01/2038 | Utility Main Contingency | 01/01/2035 | 3:00 | 5418.33
49035.91
Year: 2039
01/01/2039 | Foundation Repair Contingency | 01/01/2035 | 4:00 | 27904.42
01/01/2039 | Streets-Asphalt Seal Coating | 01/01/2034 | 5:00 | 20509.75
01/01/2039 | Unit Deck Repair & Replacement | 01/01/2034 | 5:00 | 27904.42
76318.59
Year: 2040
01/01/2040 | Landscape- Capital Maintenance & Upgrades | 01/01/2038 | 2:00 | 19161.03
01/01/2040 | Retaining Walls Repair and Replacement | 01/01/2030 | 10:00 | 9580.52
01/01/2040 | Sectional Siding/Trim Repair/Replacement | 01/01/2033 | 7:00 | 9580.52
01/01/2040 | Signage- Street & Address Replacement | 01/01/2025 | 15:00 | 5748.31
01/01/2040 | Streets- Asphalt Repair- Patching and Cracks | 01/01/2035 | 5:00 | 9580.52
53650.9
Year: 2041
01/01/2041 | Garage- Maintenance/Repair Contingency | 01/01/2036 | 5:00 | 5920.76
01/01/2041 | Sectional Siding/Trim Repair/Replacement | 01/01/2034 | 7:00 | 9867.93
01/01/2041 | Utility Main Contingency | 01/01/2038 | 3:00 | 5920.76
21709.45
Year: 2042
01/01/2042 | Buildling Staining- Residence Units | 01/01/2032 | 10:00 | 55901.84
01/01/2042 | Fence Repair Contingency | 01/01/2037 | 5:00 | 2032.79
01/01/2042 | Lanscape- Capital Maintenance & Upgrades | 01/01/2040 | 2:00 | 20327.94
01/01/2042 | Reserve Study Updates | 01/01/2038 | 4:00 | 6098.38
01/01/2042 | Sectional Siding/Trim Repair/Replacement | 01/01/2035 | 7:00 | 10163.97
94524.92
Year: 2043
01/01/2043 | Buildling Staining- Residence Units | 01/01/2033 | 10:00 | 57578.89
01/01/2043 | Common Sidewalks- Sectional Replacement | 01/01/2038 | 5:00 | 12876.73
01/01/2043 | Foundation Repair Contingency | 01/01/2039 | 4:00 | 31406.67
01/01/2043 | Roof/Gutter Replacements | 01/01/2018 | 25:00 | 41456.8
01/01/2043 | Sectional Siding/Trim Repair/Replacement | 01/01/2036 | 7:00 | 10468.89
01/01/2043 | Streets- Asphalt Resurfacing | 01/01/2023 | 20:00 | 269312.19
432100.17
Year: 2044
01/01/2044 | Buildling Staining- Residence Units | 01/01/2034 | 10:00 | 59306.26
01/01/2044 | Lanscape- Capital Maintenance & Upgrades | 01/01/2042 | 2:00 | 21565.91
01/01/2044 | Roof/Gutter Replacements | 01/01/2019 | 25:00 | 115161.97
01/01/2044 | Sectional Siding/Trim Repair/Replacement | 01/01/2037 | 7:00 | 10782.96
01/01/2044 | Streets- Asphalt Resurfacing | 01/01/2039 | 5:00 | 23776.42
01/01/2044 | Unit Deck Repair & Replacement | 01/01/2039 | 5:00 | 32348.87
01/01/2044 | Utility Main Contingency | 01/01/2041 | 3:00 | 6469.77
269412.16
Year: 2045
01/01/2045 | Buildling Staining- Residence Units | 01/01/2035 | 10:00 | 61085.45
01/01/2045 | Sectional Siding/Trim Repair/Replacement | 01/01/2038 | 7:00 | 11106.45
01/01/2045 | Streets- Asphalt Repair- Patching and Cracks | 01/01/2040 | 5:00 | 11106.45
83298.35
Year: 2046
01/01/2046 | Buildling Staining- Residence Units | 01/01/2036 | 10:00 | 62918.01
01/01/2046 | Building Staining- Garages | 01/01/2036 | 10:00 | 16473.08
01/01/2046 | Garage- Roof Replacement | 01/01/2021 | 25:00 | 41182.7
01/01/2046 | Garages- Maintenance/Repair Contingency | 01/01/2041 | 5:00 | 6863.78
01/01/2046 | Landscape- Capital Maintenance & Upgrades | 01/01/2044 | 2:00 | 22879.28
01/01/2046 | Observation Deck | 01/01/2026 | 20:00 | 54910.26
01/01/2046 | Reserve Study Updates | 01/01/2042 | 4:00 | 6863.78
01/01/2046 | Roof/Gutter Replacements | 01/01/2021 | 25:00 | 126293.61
338384.5
Year: 2047
01/01/2047 | Building Staining- Residence Units | 01/01/2037 | 10:00 | 64805.55
01/01/2047 | Building Staining- Garages | 01/01/2037 | 10:00 | 16967.27
01/01/2047 | Fence Repair Contingency | 01/01/2042 | 5:00 | 2356.57
01/01/2047 | Foundation Repair Contingency | 01/01/2043 | 4:00 | 35348.48
01/01/2047 | Garage- Roof Replacement | 01/01/2022 | 25:00 | 46660
01/01/2047 | Roof/Gutter Replacements | 01/01/2022 | 25:00 | 79180.6
01/01/2047 | Sectional Siding/Trim Repair/Replacement | 01/01/2040 | 7:00 | 11782.83
01/01/2047 | Utility Main Contingency | 01/01/2044 | 3:00 | 7069.7
264171
2018-2023 | Total costs for deffered maintenance |  |  | 339987.04

## 2018 Summary RSI
Reserve Item | Date | Basis Cost | Quantity | Current Cost | Est. Life | Adj. Life | Rem. Life | Future Cost
Bulidling Staining- Residence Units | 1/22-1/27 | 2500 | 66 Units | 165000 | 10:00 | 10:00 | 6:06 | 200206
Building Staining- Garages | 1/26-1/27 | 1800 | 8 Allowance | 14400 | 10:00 | 10:00 | 8:06 | 18515
Common Sidewalks- Sectional Replacement | 1/2018 | 10 | 615 Square Feet | 6150 | 5:00 | 7:00 | 0:00 | 6150
Fence Repair- Contingency | 1/2022 | 1000 | 1 Allowance | 1000 | 5:00 | 5:00 | 4:00 | 1125
Foundation Repair- Contingency | 1/2019 | 15000 | 1 Allowance | 15000 | 4:00 | 4:00 | 1:00 | 15450
Garage- Roof Replacement | 1/21-1/24 | 300 | 234 Squares | 70200 | 25:00 | 25:00 | 4:05 | 80015
Garages- Maintenance/Repair Contin | 1/2021 | 3,00 | 1 Allowance | 3000 | 5:00 | 5:00 | 3:00 | 3278
Landscape- Capital Mainenance & Upgrades | 1/2020 | 10000 | 1 Allowance | 10000 | 2:00 | 5:00 | 2:00 | 10609
Mailbox Stations | 1/2028 | 600 | 4 Each | 2400 | 20:00 | 20:00 | 10:00 | 3225
Observation Deck | 1/2026 | 24000 | 1 Allowance | 24000 | 20:00 | 20:00 | 8:00 | 30402
Reserve Study Updates | 1/2022 | 3000 | 1 Allowance | 3000 | 4:00 | 4:00 | 4:00 | 3376
Retaining Walls Repaid and Replacement | 1/2020 | 5000 | 1 Partial | 5000 | 10:00 | 10:00 | 2:00 | 5304
Roof/Gutter Replacement | 1/18-1/26 | 300 | 744 Squares | 223200 | 25:00 | 25:00 | 3:09 | 250463
Sectional Siding/Trim Repair/Replacement | 1/19-1/24 | 5000 | 6 Allowance | 30000 | 7:00 | 7:00 | 3:06 | 33312
Signage- Street and Address Replacement | 1/2025 | 3000 | 1 Total Re | 3000 | 15:00 | 15:00 | 7:00 | 3689
Streets- Asphalt Repair- Patching and Crack Seal | 1/2020 | 5000 | 1 Allowance | 5000 | 5:00 | 5:00 | 2:00 | 5304
Streets- Asphalt Resurfacing | 1/2023 | 1 | 73,500 Sq Ft | 128625 | 20:00 | 20:00 | 5:00 | 149111
Streets- Asphalt Seal Coating | 1/2024 | 0 | 73,500 Sq Ft | 11025 | 5:00 | 9:00 | 6:00 | 13164
Unit Deck Repair & Replacement | 1/2019 | 15000 | 1 Allowance | 15000 | 5:00 | 5:00 | 1:00 | 15450
Utility Main Contingency | 1/2020 | 3<000 | 1 Allowance | 3000 | 3:00 | 3:00 | 2:00 | 3182

## 2018 Data RSI
Expidenture |  |  |  |  | Projects that have not been completed highlighted in yellow.
Date | Reserve Item | Service Date | Estimated Life | Expidenture | Notes
Year: 2018
01/01/2018 | Common Sidewalks- Sectional Replacement | 01/01/2011 | 7:00 | 6150
01/01/2018 | Roof/Gutter Replacements | 01/01/1993 | 25:00 | 19800 | gutter replacements didn't happen
25950
Year: 2019
01/01/2019 | Foudation Repair Contingency | 01/01/2015 | 4:00 | 15450
01/01/2019 | Roof/Gutter Replacements | 01/01/1994 | 25:00 | 55002 | gutter replacements didn't happen
01/01/2019 | Sectional Siding/Trim Repair/Replacement | 01/01/2012 | 7:00 | 5150
01/01/2019 | Unit Deck Repair & Replacement | 01/01/2014 | 5:00 | 15450
91052
Year: 2020
01/01/2020 | Landscape- Capital Maintenance & Upgrades | 01/01/2015 | 5:00 | 10609
01/01/2020 | Retaining Walls Repair and Replacement | 01/01/2010 | 10:00 | 5304.5
01/01/2020 | Sectional Siding/Trim Repair/Replacement | 01/01/2013 | 7:00 | 5304.5
01/01/2020 | Streets-Asphalt Repair-Patching and Cracks | 01/01/2015 | 5:00 | 5304.5
01/01/2020 | Utility Main Contingency | 01/01/2017 | 3:00 | 3182.7
29705.2
Year: 2021
01/01/2021 | Garage- Roof Replacement | 01/01/1996 | 25:00 | 19669.09
01/01/2021 | Garages-Maintenance/Repair Contingency | 01/01/2016 | 5:00 | 3278.18
01/01/2021 | Roof/Gutter Replacements | 01/01/1996 | 25:00 | 60318.53 | gutter replacements didn't happen
01/01/2021 | Sectional Siding/Trim Repair/Replacement | 01/01/2014 | 7:00 | 5463.64
88729.44
Year: 2022
01/01/2022 | Building Staining- Residence Units | 01/01/2012 | 10:00 | 30951.49
01/01/2022 | Fence Repair Contingency | 01/01/2017 | 5:00 | 1125.51
01/01/2022 | Garage- Roof Replacement | 01/01/1997 | 25:00 | 22285.07
01/01/2022 | Lanscape- Capital Maintenance & Upgrades | 01/01/2020 | 2:00 | 11255.09
01/01/2022 | Reserve Study Updates | 01/01/2018 | 4:00 | 3376.53
01/01/2022 | Roof/Gutter Replacements | 01/01/1997 | 25:00 | 37817.1 | gutter replacements didn't happen
01/01/2022 | Sectional Siding/Trim Repair/Replacement | 01/01/2015 | 7:00 | 5627.54
112438.33
Year: 2023
01/01/2023 | Building Staining- Residence Units | 01/01/2013 | 10:00 | 31880.04
01/01/2023 | Common Sidewalks- Sectional Replacement | 01/01/2018 | 5:00 | 7129.54
01/01/2023 | Foundation Repair Contingency | 01/01/2019 | 4:00 | 17389.11
01/01/2023 | Garage- Roof Replacement | 01/01/1998 | 25:00 | 20866.93
01/01/2023 | Sectional Siding/Trim Repair/Replacement | 01/01/2016 | 7:00 | 5796.37
01/01/2023 | Streets- Asphalt Resurfacing | 01/01/2003 | 20:00 | 149111.63
01/01/2023 | Utility Main Contingency | 01/01/2020 | 3:00 | 3477.82
235651.44
Year: 2024
01/01/2024 | Building Staining- Residence Units | 01/01/2014 | 10:00 | 32836.44
01/01/2024 | Garage- Roof Replacement | 01/01/1999 | 25:00 | 17194.35
01/01/2024 | Lanscape- Capital Maintenance & Upgrades | 01/01/2022 | 2:00 | 11940.52
01/01/2024 | Sectional Siding/Trim Repair/Replacement | 01/01/2017 | 7:00 | 5970.26
01/01/2024 | Streets-Asphalt Seal Coating | 01/01/2015 | 9:00 | 13164.43
01/01/2024 | Unit Deck Repair & Replacement | 01/01/2019 | 5:00 | 17910.78
99016.78
Year:2025
01/01/2025 | Buildling Staining- Residence Units | 01/01/2015 | 10:00 | 33821.53
01/01/2025 | Signage- Street & Address Replacement | 01/01/2010 | 15:00 | 3689.62
01/01/2025 | Streets- Asphalt Repair- Patching and Cracks | 01/01/2020 | 5:00 | 6149.37
43660.52
Year: 2026
01/01/2026 | Building Staining- Residence Units | 01/01/2016 | 10:00 | 34836.18
01/01/2026 | Building Staining- Garages | 01/01/2016 | 10:00 | 9120.74
01/01/2026 | Garages- Maintenance/Repair Contingency | 01/01/2021 | 5:00 | 3800.31
01/01/2026 | Landscape- Capital Maintenance & Upgrades | 01/01/2024 | 2:00 | 12667.7
01/01/2026 | Observation Deck | 01/01/2006 | 20:00 | 30402.48
01/01/2026 | Reserve Study Updates | 01/01/2022 | 4:00 | 3800.31
01/01/2026 | Roof/Gutter Replacements | 01/01/2001 | 25:00 | 77526.33
01/01/2026 | Sectional Siding/Trim Repair/Replacement | 01/01/2019 | 7:00 | 6333.85
01/01/2026 | Utility Main Contingency | 01/01/2023 | 3:00 | 3800.31
182288.21
Year: 2027
01/01/2027 | Building Staining- Residence Units | 01/01/2017 | 10:00 | 35881.26
01/01/2027 | Building Staining- Garages | 01/01/2017 | 10:00 | 9394.37
01/01/2027 | Fence Repair Contingency | 01/01/2022 | 5:00 | 1304.77
01/01/2027 | Foundation Repair Contingency | 01/01/2023 | 4:00 | 19571.6
01/01/2027 | Sectional Siding/Trim Repair/Replacement | 01/01/2020 | 7:00 | 6523.87
72649.23
Year: 2028
01/01/2028 | Common Sidewalks- Sectional Replacement | 01/01/2023 | 5:00 | 8265.09
01/01/2028 | Lanscape- Capital Maintenance & Upgrades | 01/01/2026 | 2:00 | 13439.16
01/01/2028 | Mailbox Stations | 01/01/2008 | 20:00 | 3225.4
01/01/2028 | Sectional Siding/Trim Repair/Replacement | 01/01/2021 | 7:00 | 6719.58
31649.23
YearL 2029
01/01/2029 | Sectional Siding/Trim Repair/Replacement | 01/01/2022 | 7:00 | 6921.17
01/01/2029 | Streets-Asphalt Seal Coating | 01/01/2024 | 5:00 | 15261.18
01/01/2029 | Unit Deck Repair & Replacement | 01/01/2024 | 5:00 | 20763.51
01/01/2029 | Utility Main Contingency | 01/01/2026 | 3:00 | 4152.7
47098.56
Year: 2030
01/01/2030 | Landscape- Capital Maintenance & Upgrades | 01/01/2028 | 2:00 | 14257.61
01/01/2030 | Reserve Study Updates | 01/01/2026 | 4:00 | 4277.28
01/01/2030 | Retaining Walls Repair and Replacement | 01/01/2020 | 10:00 | 7128.8
01/01/2030 | Sectional Siding/Trim Repair/Replacement | 01/01/2023 | 7:00 | 7128.8
01/01/2030 | Streets- Asphalt Repair- Patching and Cracks | 01/01/2025 | 5:00 | 7128.8
39921.29
Year: 2031
01/01/2031 | Foundation Repair Contingency | 01/01/2027 | 4:00 | 22028.01
01/01/2031 | Garages- Maintenance/Repair Contingency | 01/01/2026 | 5:00 | 4405.6
01/01/2031 | Sectional Siding/Trim Repair/Replacement | 01/01/2024 | 7:00 | 7342.67
33776.28
Year: 2032
01/01/2032 | Building Staining- Residence Units | 01/01/2022 | 10:00 | 41596.22
01/01/2032 | Fence Repair Contingency | 01/01/2027 | 5:00 | 1512.59
01/01/2032 | Landscape- Capital Mainenance & Upgrades | 01/01/2030 | 2:00 | 15125.9
01/01/2032 | Utility Main Contingency | 01/01/2029 | 3:00 | 4537.77
62772.48
Year: 2033
01/01/2033 | Building Staining- Residence Units | 01/01/2023 | 10:00 | 42844.1
01/01/2033 | Common Sidewalks- Sectional Replacement | 01/01/2028 | 5:00 | 9581.5
01/01/2033 | Sectional Siding/Trim Repair/Replacement | 01/01/2026 | 7:00 | 7789.84
60215.44
Year: 2034
01/01/2034 | Buildling Staining- Residence Units | 01/01/2024 | 10:00 | 44129.43
01/01/2034 | Landscape- Capital Maintenance & Upgrades | 01/01/2032 | 2:00 | 16047.06
01/01/2034 | Reserve Study Updates | 01/01/2030 | 4:00 | 4814.12
01/01/2034 | Sectional Siding/Trim Repair/Replacement | 01/01/2027 | 7:00 | 8023.53
01/01/2034 | Streets- Asphalt Seal Coating | 01/01/2029 | 5:00 | 17961.89
01/01/2034 | Unit Deck Repair & Replacement | 01/01/2029 | 5:00 | 24070.6
114776.63
Year: 2035
01/01/2035 | Buildling Staining- Residence Units | 01/01/2025 | 10:00 | 45453.31
01/01/2035 | Building Staining- Garages | 01/01/2031 | 4:00 | 24792.71
01/01/2035 | Garages- Maintenance/Repair Contingency | 01/01/2028 | 7:00 | 8264.24
01/01/2035 | Lanscape- Capital Maintenance & Upgrades | 01/01/2030 | 5:00 | 8264.24
01/01/2035 | Sectional Siding/Trim Repair/Replacement | 01/01/2032 | 3:00 | 4958.54
91733.04
Year: 2036
01/01/2036 | Building Staining- Residence Units | 01/01/2026 | 10:00 | 46816.91
01/01/2036 | Building Staining- Garages | 01/01/2026 | 10:00 | 12257.52
01/01/2036 | Garages- Maintenance/Repair Contingency | 01/01/2031 | 5:00 | 5107.3
01/01/2036 | Lanscape- Capital Maintenance & Upgrades | 01/01/2034 | 2:00 | 17024.33
01/01/2036 | Sectional Siding/Trim Repair/Replacement | 01/0/2029 | 7:00 | 8512.17
89718.23
Year: 2037
01/01/2037 | Building Staining- Residence Units | 01/01/2027 | 10:00 | 48221.42
01/01/2037 | Building Staining- Garages | 01/01/2027 | 10:00 | 12625.24
01/01/2037 | Fence Repair- Contingency | 01/01/2032 | 5:00 | 1753.51
01/01/2037 | Sectional Siding/Trim Repair/Replacement | 01/01/2030 | 7:00 | 8767.53
71367.7
Year: 2038
01/01/2038 | Common Sidewalks- Sectional Replacement | 01/01/2033 | 5:00 | 11107.58
01/01/2038 | Lanscape- Capital Maintenance & Upgrades | 01/01/2036 | 2:00 | 18061.11
01/01/2038 | Reserve Study Updates | 01/01/2034 | 4:00 | 5418.33
01/01/2038 | Sectional Siding/Trim Repair/Replacement | 01/01/2031 | 7:00 | 9030.56
01/01/2038 | Utility Main Contingency | 01/01/2035 | 3:00 | 5418.33
49035.91
Year: 2039
01/01/2039 | Foundation Repair Contingency | 01/01/2035 | 4:00 | 27904.42
01/01/2039 | Streets-Asphalt Seal Coating | 01/01/2034 | 5:00 | 20509.75
01/01/2039 | Unit Deck Repair & Replacement | 01/01/2034 | 5:00 | 27904.42
76318.59
Year: 2040
01/01/2040 | Landscape- Capital Maintenance & Upgrades | 01/01/2038 | 2:00 | 19161.03
01/01/2040 | Retaining Walls Repair and Replacement | 01/01/2030 | 10:00 | 9580.52
01/01/2040 | Sectional Siding/Trim Repair/Replacement | 01/01/2033 | 7:00 | 9580.52
01/01/2040 | Signage- Street & Address Replacement | 01/01/2025 | 15:00 | 5748.31
01/01/2040 | Streets- Asphalt Repair- Patching and Cracks | 01/01/2035 | 5:00 | 9580.52
53650.9
Year: 2041
01/01/2041 | Garage- Maintenance/Repair Contingency | 01/01/2036 | 5:00 | 5920.76
01/01/2041 | Sectional Siding/Trim Repair/Replacement | 01/01/2034 | 7:00 | 9867.93
01/01/2041 | Utility Main Contingency | 01/01/2038 | 3:00 | 5920.76
21709.45
Year: 2042
01/01/2042 | Buildling Staining- Residence Units | 01/01/2032 | 10:00 | 55901.84
01/01/2042 | Fence Repair Contingency | 01/01/2037 | 5:00 | 2032.79
01/01/2042 | Lanscape- Capital Maintenance & Upgrades | 01/01/2040 | 2:00 | 20327.94
01/01/2042 | Reserve Study Updates | 01/01/2038 | 4:00 | 6098.38
01/01/2042 | Sectional Siding/Trim Repair/Replacement | 01/01/2035 | 7:00 | 10163.97
94524.92
Year: 2043
01/01/2043 | Buildling Staining- Residence Units | 01/01/2033 | 10:00 | 57578.89
01/01/2043 | Common Sidewalks- Sectional Replacement | 01/01/2038 | 5:00 | 12876.73
01/01/2043 | Foundation Repair Contingency | 01/01/2039 | 4:00 | 31406.67
01/01/2043 | Roof/Gutter Replacements | 01/01/2018 | 25:00 | 41456.8
01/01/2043 | Sectional Siding/Trim Repair/Replacement | 01/01/2036 | 7:00 | 10468.89
01/01/2043 | Streets- Asphalt Resurfacing | 01/01/2023 | 20:00 | 269312.19
432100.17
Year: 2044
01/01/2044 | Buildling Staining- Residence Units | 01/01/2034 | 10:00 | 59306.26
01/01/2044 | Lanscape- Capital Maintenance & Upgrades | 01/01/2042 | 2:00 | 21565.91
01/01/2044 | Roof/Gutter Replacements | 01/01/2019 | 25:00 | 115161.97
01/01/2044 | Sectional Siding/Trim Repair/Replacement | 01/01/2037 | 7:00 | 10782.96
01/01/2044 | Streets- Asphalt Resurfacing | 01/01/2039 | 5:00 | 23776.42
01/01/2044 | Unit Deck Repair & Replacement | 01/01/2039 | 5:00 | 32348.87
01/01/2044 | Utility Main Contingency | 01/01/2041 | 3:00 | 6469.77
269412.16
Year: 2045
01/01/2045 | Buildling Staining- Residence Units | 01/01/2035 | 10:00 | 61085.45
01/01/2045 | Sectional Siding/Trim Repair/Replacement | 01/01/2038 | 7:00 | 11106.45
01/01/2045 | Streets- Asphalt Repair- Patching and Cracks | 01/01/2040 | 5:00 | 11106.45
83298.35
Year: 2046
01/01/2046 | Buildling Staining- Residence Units | 01/01/2036 | 10:00 | 62918.01
01/01/2046 | Building Staining- Garages | 01/01/2036 | 10:00 | 16473.08
01/01/2046 | Garage- Roof Replacement | 01/01/2021 | 25:00 | 41182.7
01/01/2046 | Garages- Maintenance/Repair Contingency | 01/01/2041 | 5:00 | 6863.78
01/01/2046 | Landscape- Capital Maintenance & Upgrades | 01/01/2044 | 2:00 | 22879.28
01/01/2046 | Observation Deck | 01/01/2026 | 20:00 | 54910.26
01/01/2046 | Reserve Study Updates | 01/01/2042 | 4:00 | 6863.78
01/01/2046 | Roof/Gutter Replacements | 01/01/2021 | 25:00 | 126293.61
338384.5
Year: 2047
01/01/2047 | Building Staining- Residence Units | 01/01/2037 | 10:00 | 64805.55
01/01/2047 | Building Staining- Garages | 01/01/2037 | 10:00 | 16967.27
01/01/2047 | Fence Repair Contingency | 01/01/2042 | 5:00 | 2356.57
01/01/2047 | Foundation Repair Contingency | 01/01/2043 | 4:00 | 35348.48
01/01/2047 | Garage- Roof Replacement | 01/01/2022 | 25:00 | 46660
01/01/2047 | Roof/Gutter Replacements | 01/01/2022 | 25:00 | 79180.6
01/01/2047 | Sectional Siding/Trim Repair/Replacement | 01/01/2040 | 7:00 | 11782.83
01/01/2047 | Utility Main Contingency | 01/01/2044 | 3:00 | 7069.7
264171
2018-2023 | Total costs for deffered maintenance |  |  | 339987.04 | This does not include any gutter replacements